## timeline_v1
Final expected output | 1. SIPLIPv2 website (instance repository)
2. Paper
Timeline (tentative due: ~ June 1)
Task |  | Expected output | February |  | March |  |  |  | April |  |  |  | May
|  |  | 2/19-23 | 2/26-3/2 | 3/5-9 | 3/12-16 | 3/19-23 | 3/26-30 | 4/2-6 | 4/9-13 | 4/16-20 | 4/23-27 | 4/30-5/4 | 5/7-11 | 5/14-18 | 5/21-25 | 5/28-6/1
Survey | Know what SIP is
| Study & run existing Instances (SIPLIPv1) with solvers & known algorithms | Summary of each instance
| Categorize SIP | SIP taxonomy
| Come up with “Measure of Goodness (or conformance)" for SIP instances | Measures
| Identify "Family" (area) for which dedicated test sets should be included | Family
Format | Define “Format” in which the library will be provided | Format: Library
| Define “Format” that will be used for CFI (call for instances) | Format: CFI
Data | Call For Instances (instances should be submitted in the predefined format) | Temporary website
| Collect instances from available sources: Literature, Web, Peers, … | Data collection (unarranged)
| Preprocess the collected instances (documentation, formatting) | Data collection (arranged)
| Categorize data in "Family" | Categorized list
Experiment | Conduct experiments with collected instances & solvers & well-known algorithms | Experimental results
| Summarize the result for each instance | Summary for experiments
| Classify the instances into three categories (easy, hard, open) | Classified list
Implement web | Upload the outputs on website | SIPLIPv2 website
Writing | 1. Introduction: What SIP is, Why SIPLIPv2 is required, What we did | Manuscript
2. Literature Review: SIPLIPv1, another approaches for evaluating SIP solving algorithms
3. Methods: How we construct SIPLIPv2
4. Instance catalog
5. Solver & Algorithm performance for benchmarking
6. Conclusion

## timeline_v2
Final expected output | 1. Manuscript
1. SIPLIPv2 website (instance repository) (after submission0
Timeline (tentative due: ~ June 1)
Task |  | Expected output | February |  | March |  |  |  | April |  |  |  | May
|  |  | 2/19-23 | 2/26-3/2 | 3/5-9 | 3/12-16 | 3/19-23 | 3/26-30 | 4/2-6 | 4/9-13 | 4/16-20 | 4/23-27 | 4/30-5/4 | 5/7-11 | 5/14-18 | 5/21-25 | 5/28-6/1
Survey | Know what SIP is
| Study & run existing Instances (SIPLIPv1) with solvers & known algorithms | Summary of each instance
| Categorize SIP | SIP taxonomy
| Come up with “Measure of Goodness (or conformance)" for SIP instances | Measures
| Identify "Family" (area) for which dedicated test sets should be included | Family
Data | Collect instances from available sources: Literature, Web, Peers, … | Data collection (unarranged)
| Preprocess the collected instances (documentation, formatting) | Data collection (arranged)
| Categorize data in "Family" | Categorized list
Experiment | Conduct experiments with collected instances & solvers & well-known algorithms | Experimental results
| Summarize the result for each instance | Summary for experiments
| Classify the instances into three categories (easy, hard, open) | Classified list
Writing | 1. Introduction: What SIP is, Why SIPLIPv2 is required, What we did | Manuscript
2. Literature Review: SIPLIPv1, another approaches for evaluating SIP solving algorithms
3. Methods: How we construct SIPLIPv2
4. Instance catalog
5. Solver & Algorithm performance for benchmarking
6. Conclusion
Implement web | Upload the outputs on website | SIPLIPv2 website

## timeline_v3
Final expected output | 1. Manuscript
Task |  | Expected output | April |  |  |  | May
|  |  | 4/2-6 | 4/9-13 | 4/16-20 | 4/23-27 | 4/30-5/4 | 5/7-11 | 5/14-18 | 5/21-25 | 5/28-6/1
Experiment | Preprocess Julia codes (sizes)
Decide what to analyze: expected shape of figures, tables
Design of Experiment: Determine instances to generate, time limit
Run experiments on workstation (using Julia interface for storing result data)