## SIPLIB
Business days | Task | Detail level 1 | Detail level 2 | Detail level 3
Feb 5 – 16 | Practice JuMP modeling | Implement data center planning problem (Networks SI)
| Preview Power models | Read two IEEE power system papers
Come up with research direction during in Argonne
Feb 19 – Mar 30 | Preview SIP | Understand purpose, methods, formulation, structure
| Survey SIPLIB 1.0 | Comprehend each problem
| Skim MIPLIB 2010 | Grasp purpose, Structure, Methods
Survey new problems
| Implement SIPLIB 1.0 problems | Problem: MPTSPs | Model implementation | Fix wrong constraints (subtour elimination)
|  |  | Data generation | Guess missing procedure & develop my own way (need validation)
|  |  | Instance generation | for both SIPLIB 1.0 and 2.0
|  | Problem: SIZES | Model implementation | Fix formulation (due to unclear) (need validation)
|  |  | Instance generation | Develop my own scenario data generation (need validation)
|  | Problem: SMKP | Model implementation
Instance generation
| Start writing draft | Construct contents structure: Sec1 – Sec 7
| (wrote approximately 20 pages) | Sec1: Introduction
|  | Appendix: Problem description | DCAP | Reference is clear
|  | (modify notations for consistency) | MPTSPs | time consuming part: data generation
|  |  | SIZES | time consuming part: data generation
|  |  | SMKP | time consuming part: problem explanation
|  |  | SSLP | Reference is clear except some data generation
|  |  | SUCW | Adopt Dr. Kim’s LaTeX script
|  | Sec3: Summary | tables | Determine problem type (based on MIPLIB), instance naming rule
|  | Sec2: SIP Formulation | Adopt Dr. Kim’s notations (modify some for consistency) | Make notation table for readability
| Tidy up Julia codes for experiments | Reconstruct files into: main, models, functions, types | xxxx_main.jl: for generating SMPS files
xxxx_models.jl: define JuMP models
Xxxx_functions.jl: some functions used to construct JuMP object
xxxx_types.jl: mainly for storing data
| Figure out DSP error | CPLEX 12.8 has compatibility issue with DSP | dynamic linker needs to be specified manually | Open an issue on SIPLIB GitLab
Apr 2 – 6 | Run DSP for practice | Standalone solver
Julia Interface
MPI
Benders (fail due to SCIP)
| Figure out DCAP error | logical constraint is wrong (open an issue on GitLab)
Find bug in SmpsWriter.jl
| Find problem in SMKP instances | DSP(dd) cannot solve whereas DSP(de) can solve
Apr 9 – 14